|  | Jasper and Newton County Continuum of Care FY2026 CoC NOFO Local Competition Timeline |
| --- | --- |

All local submissions are due by 5:00 PM Central Time unless otherwise stated. Dates may be revised by the CoC if HUD issues changes or technical guidance.

HUD deadline check and local safeguards

| Checkpoint | HUD / process requirement | Local timeline response |
| --- | --- | --- |
| HUD NOFO deadline | 08/26/2026, 8:00 PM Eastern Time | Local internal submission target is 08/21/2026; final HUD deadline retained as external deadline. |
| 15-day applicant notice | Written notice must be sent no later than 15 days before the HUD deadline. | Final priority list and written notifications scheduled for 08/11/2026. |
| Public posting | CoC Application, Priority Listing, and project listings should be publicly posted before final submission. | Public posting scheduled for 08/17/2026; preserve dated screenshots. |
| Local competition documentation | Document public notice, scoring, ranking, appeals, threshold review, and application submission records. | Timeline includes local review, appeal window, applicant revisions, and records checklist. |

Local competition timeline

| Date | Activity / deadline | Responsible | Place / notes |
| --- | --- | --- | --- |
| Mon 6/1 | HUD releases FY2026 CoC Competition and YHDP Grants NOFO. | HUD | Grants.gov / e-snaps. Official HUD deadline is 08/26/2026. |
| Tue 6/2 | Send NOFO release notice, links, and initial local competition alert to CoC membership, current project contacts, CoC Board, and interested stakeholders. | Collaborative Applicant / CoC Lead | Email and website. Include where updates will be posted. |
| Tue 6/9 | Post project application timeline, Letter of Intent form, available application types, and local competition overview. Distribute by email and post to The Homeless Coalition website. | Collaborative Applicant | Website and email. Public notice should show local process and due dates. |
| Tue 6/16 | Distribute renewal performance information, HMIS/comparable database reminders, and data quality review materials, if applicable. | HMIS Lead / Collaborative Applicant | Email; optional office hours. Allow time to correct data or explain data quality issues. |
| Wed 6/16 | Rank and Review Committee updates forms, review process, local priorities, scoring tool, appeals process, and threshold screening plan. | Rank and Review Committee | Committee meeting. Handwritten local target date. |
| By Fri 6/19 | Finalize and post local review/ranking procedures, score tool, LOI instructions, project application instructions, and applicant guidance. | Collaborative Applicant / Rank and Review Chair | Website and email. Keep screenshots for HUD documentation. |
| Wed 6/24 | Letter of Intent due for all project types as applicable, including new, renewal, reallocation, DV bonus, consolidation, transition/replacement, planning, HMIS, and YHDP projects. | Project Applicants | Email submission. Use to plan local review workload and identify project types. |
| By Fri 6/26 | Send local application packet, budget instructions, required attachments, and e-snaps guidance to applicants that submitted LOIs. | Collaborative Applicant | Email and website. Include contacts for technical questions. |
| Mon 7/6 | NOFO applicant training and application instructions released; training available for new and renewal applicants. | Collaborative Applicant; HMIS Lead | Virtual / recorded. Cover e-snaps, local packet, scorecard, attachments, and deadlines. |
| Wed 7/8 | Application portal/process opens for project applications and local packet submissions. | Collaborative Applicant | e-snaps and local submission instructions. |
| Wed 7/15 | Optional applicant office hours and staff Q&A for process and technical questions. Staff may answer process questions but not project-specific scoring advice. | Collaborative Applicant | Virtual. Recommended final Q&A before submission week. |
| Tue 7/21 | Agency project applications due in e-snaps. Applicants should submit the project application in e-snaps, export the PDF, and prepare the local packet. | Project Applicants | e-snaps. Handwritten local target date. |
| Fri 7/24 | Applicant submits Rank and Review packet/forms to committee, including exported e-snaps PDF, local application, budget, attachments, match/source documentation, and threshold materials. | Project Applicants | Email, mail, or in person as directed. Handwritten local target date. |
| Fri 7/24 | Projects that do not meet threshold review criteria are notified and are not advanced to Rank and Review Panel. | Collaborative Applicant | Written notice and/or phone call. Include reason for threshold decision. |
| Sat 7/25 - Sun 8/2 | Rank and Review Committee reviews project applications, scorecards, local packets, budgets, and supporting documents independently. | Rank and Review Committee | Document review. Handwritten local review window. |
| Mon 8/3 | Rank and Review Committee meeting to score, rank, and develop preliminary priority listing and funding recommendations. | Rank and Review Committee | In person or virtual. Handwritten priority-list date aligns with review window. |
| Mon 8/3 | Distribute/post Preliminary Priority List and notify applicants of preliminary ranking, reductions, rejection, or reallocation recommendations. | Collaborative Applicant / Rank and Review Chair | Website and email. Starts appeal window. |
| Tue 8/4 | Written appeals due to Rank and Review Committee Chair by 5:00 PM Central Time. | Applicants | Email to designated appeal contact. Handwritten local target date. |
| Fri 8/7 | Appeals reviewed by Rank and Review Committee; appeal determinations documented. | Rank and Review Committee | Committee review. Handwritten local target date. |
| Tue 8/11 | Final Priority List distributed/posted; written notice sent to all applicants identifying accepted and ranked, rejected, or reduced applications and, if applicable, reasons. | Collaborative Applicant / Rank and Review Chair | Website and email to all applicants. This preserves the HUD 15-day notice requirement. |
| Wed 8/12 - Fri 8/14 | Applicants revise e-snaps project applications as directed due to recommended funding reductions, technical review clarification, appeal outcomes, or rank/review conditions. | Project Applicants | e-snaps. No changes after final applicant due date unless directed. |
| Fri 8/14 | Final applicant deadline to complete project applications in e-snaps for Collaborative Applicant review. | Project Applicants | e-snaps. Recommended internal lock date. |
| Mon 8/17 | Post draft CoC Consolidated Application, Priority Listing, and project listings for public review, including accepted/ranked, noncompetitive, and rejected projects as applicable. | Collaborative Applicant | The Homeless Coalition website; email notice. Keep dated screenshots. |
| Thu 8/20 | CoC Board reviews and votes/approves final Consolidated Application package and Priority Listing for submission. | CoC Board | Board meeting / email vote. Address final comments before internal deadline. |
| Fri 8/21 | Collaborative Applicant internal submission target: full application packet, CoC Application, Priority Listing, and ranked project applications ready/submitted in e-snaps. | Collaborative Applicant | e-snaps. Handwritten local target date; preserves buffer. |
| Mon 8/24 | No substantive local changes after this date except urgent technical corrections. HUD technical questions become emergency-focused starting two days before the deadline. | Collaborative Applicant | e-snaps / HUD support. Use for receipt review and contingency. |
| Wed 8/26 | HUD-determined final submission deadline for FY2026 CoC Consolidated Application package. | Collaborative Applicant | e-snaps. Due by 8:00 PM Eastern Time. |